## BurnDown
Week | Date | Story Points (3pts/wk) | Est. Hours (8hrs/pt) | Hours Remaining | Hours per day | Hours Logged | Hours Remaining
Thursday Wk7 | 2017-04-13 | 24 | 192 | 192 | 3.4286 | 0 | 192
| 2017-04-14 | 24 | 192 | 188.5714 | 3.4286 | 0 | 192
| 2017-04-15 | 24 | 192 | 185.1429 | 3.4286 | 0 | 192
| 2017-04-16 | 24 | 192 | 181.7143 | 3.4286 | 0 | 192
| 2017-04-17 | 24 | 192 | 178.2857 | 3.4286 | 0 | 192
| 2017-04-18 | 24 | 192 | 174.8571 | 3.4286 | 0 | 192
| 2017-04-19 | 24 | 192 | 171.4286 | 3.4286 | 0 | 192
Thursday MidSem Break | 2017-04-20 | 21 | 168 | 168 | 3.4286 | 0 | 192
| 2017-04-21 | 21 | 168 | 164.5714 | 3.4286 | 0 | 192
| 2017-04-22 | 21 | 168 | 161.1429 | 3.4286 | 0 | 192
| 2017-04-23 | 21 | 168 | 157.7143 | 3.4286 | 0 | 192
| 2017-04-24 | 21 | 168 | 154.2857 | 3.4286 | 0 | 192
| 2017-04-25 | 21 | 168 | 150.8571 | 3.4286 | 0 | 192
| 2017-04-26 | 21 | 168 | 147.4286 | 3.4286 | 0 | 192
Thursday Wk8 | 2017-04-27 | 18 | 144 | 144 | 3.4286 | 0 | 192
| 2017-04-28 | 18 | 144 | 140.5714 | 3.4286 | 8 | 184
| 2017-04-29 | 18 | 144 | 137.1429 | 3.4286 | 5 | 179
| 2017-04-30 | 18 | 144 | 133.7143 | 3.4286 | 0 | 179
| 2017-05-01 | 18 | 144 | 130.2857 | 3.4286 | 0 | 179
| 2017-05-02 | 18 | 144 | 126.8571 | 3.4286 | 0 | 179
| 2017-05-03 | 18 | 144 | 123.4286 | 3.4286 | 4 | 175
Thursday Wk9 | 2017-05-04 | 15 | 120 | 120 | 3.4286 | 0 | 175
| 2017-05-05 | 15 | 120 | 116.5714 | 3.4286 | 0 | 175
| 2017-05-06 | 15 | 120 | 113.1429 | 3.4286 | 6 | 169
| 2017-05-07 | 15 | 120 | 109.7143 | 3.4286 | 0 | 169
| 2017-05-08 | 15 | 120 | 106.2857 | 3.4286 | 0 | 169
| 2017-05-09 | 15 | 120 | 102.8571 | 3.4286 | 0 | 169
| 2017-05-10 | 15 | 120 | 99.4286 | 3.4286 | 0 | 169
Thursday Wk10 | 2017-05-11 | 12 | 96 | 96 | 3.4286 | 0 | 169
| 2017-05-12 | 12 | 96 | 92.5714 | 3.4286 | 0 | 169
| 2017-05-13 | 12 | 96 | 89.1429 | 3.4286 | 0 | 169
| 2017-05-14 | 12 | 96 | 85.7143 | 3.4286 | 0 | 169
| 2017-05-15 | 12 | 96 | 82.2857 | 3.4286 | 0 | 169
| 2017-05-16 | 12 | 96 | 78.8571 | 3.4286 | 0 | 169
| 2017-05-17 | 12 | 96 | 75.4286 | 3.4286 | 0 | 169
Thursday Wk11 | 2017-05-18 | 9 | 72 | 72 | 3.4286 | 0 | 169
| 2017-05-19 | 9 | 72 | 68.5714 | 3.4286 | 0 | 169
| 2017-05-20 | 9 | 72 | 65.1429 | 3.4286 | 0 | 169
| 2017-05-21 | 9 | 72 | 61.7143 | 3.4286 | 0 | 169
| 2017-05-22 | 9 | 72 | 58.2857 | 3.4286 | 0 | 169
| 2017-05-23 | 9 | 72 | 54.8571 | 3.4286 | 0 | 169
| 2017-05-24 | 9 | 72 | 51.4286 | 3.4286 | 0 | 169
Thursday Wk12 | 2017-05-25 | 6 | 48 | 48 | 3.4286 | 0 | 169
| 2017-05-26 | 6 | 48 | 44.5714 | 3.4286 | 0 | 169
| 2017-05-27 | 6 | 48 | 41.1429 | 3.4286 | 0 | 169
| 2017-05-28 | 6 | 48 | 37.7143 | 3.4286 | 0 | 169
| 2017-05-29 | 6 | 48 | 34.2857 | 3.4286 | 0 | 169
| 2017-05-30 | 6 | 48 | 30.8571 | 3.4286 | 0 | 169
| 2017-05-31 | 6 | 48 | 27.4286 | 3.4286 | 0 | 169
Thursday Wk13 | 2017-06-01 | 3 | 24 | 24 | 3.4286 | 0 | 169
| 2017-06-02 | 3 | 24 | 20.5714 | 3.4286 | 0 | 169
| 2017-06-03 | 3 | 24 | 17.1429 | 3.4286 | 0 | 169
| 2017-06-04 | 3 | 24 | 13.7143 | 3.4286 | 0 | 169
| 2017-06-05 | 3 | 24 | 10.2857 | 3.4286 | 0 | 169
| 2017-06-06 | 3 | 24 | 6.8571 | 3.4286 | 0 | 169
| 2017-06-07 | 3 | 24 | 3.4286 | 3.4286 | 0 | 169
Thursday Wk14 (DUE) | 2017-06-08 | 0 | 0 | 0 | 3.4286 | 0 | 169
23

## Luke
Date | Hours Worked | User Story ID | Task ID | Task | Comments
2017-04-28 | 8 | S27 | T01 | Landing Page | Experimenting with Home Page Layout
2017-04-29 | 5 | S27 | T01 | Landing Page | Additional Landing Page Formatting
2017-05-03 | 4 | S27 | T01 | Landing Page | Final Layout of Home Page (index.html)
2017-03-06 | 3 | S27 | T03 | Colour Scheme | Modifying Colour scheme of header/footer
2017-03-06 | 3 | S27 | T03 | Logo | Designed, Created and Installed Site Logo

## Jamie
Date | Hours Worked | User Story ID | Task ID | Task | Comments

## Harry
Date | Hours Worked | User Story ID | Task ID | Task | Comments